## Sheet1
Item | Description | Notes | Complexity | Status
Highest Priority (game breaking)
Options menu remake
| Spiders move to first block when hit | Unable to replicate
High Priority (significant or breaks immersion)
| Tutorials | bosshandler.cs
Music
Sound effects
You win screen
| Swinging spiders drop after a set amount of time and shouldn’t ever drop… | Because this isn't a game that needs to be complete, we're descoping this
Medium Priority (important fixes that can be worked around or require optimisation)
| sometimes on boss levels, the boss jumps real high after being hit by hypersonic | Not replicating through various replays. Not a game breaking bug either.
Low Priority (cosmetic, nice to have or potential optimisations)
| Boss particle effects bounce through ground after defeat | Not worth fixing, no one will notice or care
| game takes a long time to load on mobile | Not worth optimising, not the purpose of release
Checks (things that need to be tested)
Done (just for reference)
| death effects / physics misbehaving | 2019-03-23
| Data not saving | 2019-03-23
| Settings need to persist through sessions | 2019-03-23
| boss stalactites forming in weird ways | 2019-03-23
| spikes on boss levels aren't damaging player | 2019-03-23
| Dropstals also drops lower stals | 2019-03-23
| when boss hits ground stalactite, it shouldn’t be able to be hit again | 2019-03-23
| on boss death, player shouldn’t be getting hurt when colliding with the space it used to be in | 2019-03-23
| Level implementations (e.g. main 5 is broken) | 2019-03-23
| Tooltips are displayed even when turned off In options | 2019-03-23
| Lantern doing that weird thing again on cave entrance animation | 2019-03-23
| If menu was accessed in game, after tooltips, it appears and animates up | 2019-03-23
| crystal boss achievements, missing under 2 hits | 2019-03-23
| At 1 shield, lantern colour doesn't change on hit, and player doesn't die | 2019-03-23
| Death animation looks like a bug (but is not) - require better animation | 2019-03-23
| Rush ability | 2019-03-23
| shroom spores do nothing | 2019-05-07
| Can fall into hidden levels by hitting spikes (shield allows passthrough) | 2019-05-07
| Triggers still get triggered after activating the first time (because we can go backwards now) | 2019-05-07
| Death animation for in-game stalactites | 2019-05-07
| Death not applied when character falls through floor | 2019-05-07
| Secret path registers but event not fired | 2019-05-08
| Stop camera moving on death | 2019-05-08
| Ability and level data is only applied after reloading | 2019-05-09
| Clear data full implementation (in game has errors, different to in menu) | 2019-05-09
| Can fall through floor in boss levels | 2019-05-09
| clear bosses on boss level setup, or at end of boss level | 2019-05-09
| Wait a few seconds after boss dies before ending level | 2019-05-09
| Score being hidden after crystal boss level and not visible in next level | 2019-05-09
| Score hidden after entrance animation in boss level | 2019-05-09
| Game does not load the first time | 2019-05-15
| Clumsy is displayed over end cave piece | 2019-05-15
| boss level is too short on mobile and can see past door and cave at start | 2019-05-15
| on restart, player should face right before entering scene again | ?
| Crystals do not shatter on mobile in crystal boss room after solving | ?
| Pause game on completion (timer keeps going, can move player) | ?
| can press pause at level complete screen (even paused screen) | 2019-11-11
| restart on boss fight is buggy | 2019-11-11
| Stalactite rubble doesn't disappear | 2019-11-11
| Player enters boss levels twice (plays entrance coroutine twice?) | 2019-11-11
| on death, all buttons are shown in the dropdown menu | 2019-11-16
| on restart, the player should reset properly (e.g. retry on death bugs out) | 2019-11-16
| hypersonic was not being accessed properly | 2019-11-16
| crystal boss - so many moth essence. clean this up. | 2019-11-16
| Loading screen - removed moth | 2019-11-16
| Reset fog | 2019-11-17
| Clear spider webs on reset | 2019-11-17
| Boss moths don't disappear on restart | 2019-11-17
| Check triggers are reset properly | 2019-11-17
| Stats screen to be implemented | 2019-11-23
| Stat tracking (distance, durations etc) to be implemented | 2019-11-24
| sometimes on boss levels, jump gets stuck | 2019-11-24
| couritine on boss level to shut doors and start boss - keeps running on restart | 2019-11-24
| Main Menu title screen: Clicking "options" after "play" is buggy (switch screens) | 2019-11-24
| boss levels need to disable fog | 2019-11-25
| clumsy doesn’t show up on startup in menu | 2019-11-25
| Check level stars show up - refresh after level complete? | 2019-11-26
| switching to level select from menu - clumsy needs to follow, camera shouldn't slide | 2019-11-26
| Level select scrolling to go back to start to hide the end of the content window | 2019-11-26
| Mushroom spore angles not being reset on respawn | 2019-12-08
| Scores must be achievable | 2019-12-08
| Finish levels | 2019-12-08
Bosses get stuck on ground when dashing