## Sheet1
Item | Description | Notes | Complexity | Status
Highest Priority (game breaking)
Finish levels
Options menu remake
Bosses get stuck on ground when dashing
Spiders move to first block when hit
High Priority (significant or breaks immersion)
| Tutorials | bosshandler.cs
Scores must be achievable
Music
Sound effects
Mushroom spore angles not being reset on respawn
You win screen
Medium Priority (important fixes that can be worked around or require optimisation)
sometimes on boss levels, the boss jumps real high after being hit by hypersonic
Low Priority (cosmetic, nice to have or potential optimisations)
Boss particle effects bounce through ground after defeat
game takes a long time to load on mobile
Checks (things that need to be tested)
Done (just for reference)
| death effects / physics misbehaving | 2019-03-23
| Data not saving | 2019-03-23
| Settings need to persist through sessions | 2019-03-23
| boss stalactites forming in weird ways | 2019-03-23
| spikes on boss levels aren't damaging player | 2019-03-23
| Dropstals also drops lower stals | 2019-03-23
| when boss hits ground stalactite, it shouldn’t be able to be hit again | 2019-03-23
| on boss death, player shouldn’t be getting hurt when colliding with the space it used to be in | 2019-03-23
| Level implementations (e.g. main 5 is broken) | 2019-03-23
| Tooltips are displayed even when turned off In options | 2019-03-23
| Lantern doing that weird thing again on cave entrance animation | 2019-03-23
| If menu was accessed in game, after tooltips, it appears and animates up | 2019-03-23
| crystal boss achievements, missing under 2 hits | 2019-03-23
| At 1 shield, lantern colour doesn't change on hit, and player doesn't die | 2019-03-23
| Death animation looks like a bug (but is not) - require better animation | 2019-03-23
| Rush ability | 2019-03-23
| shroom spores do nothing | 2019-05-07
| Can fall into hidden levels by hitting spikes (shield allows passthrough) | 2019-05-07
| Triggers still get triggered after activating the first time (because we can go backwards now) | 2019-05-07
| Death animation for in-game stalactites | 2019-05-07
| Death not applied when character falls through floor | 2019-05-07
| Secret path registers but event not fired | 2019-05-08
| Stop camera moving on death | 2019-05-08
| Ability and level data is only applied after reloading | 2019-05-09
| Clear data full implementation (in game has errors, different to in menu) | 2019-05-09
| Can fall through floor in boss levels | 2019-05-09
| clear bosses on boss level setup, or at end of boss level | 2019-05-09
| Wait a few seconds after boss dies before ending level | 2019-05-09
| Score being hidden after crystal boss level and not visible in next level | 2019-05-09
| Score hidden after entrance animation in boss level | 2019-05-09
| Game does not load the first time | 2019-05-15
| Clumsy is displayed over end cave piece | 2019-05-15
| boss level is too short on mobile and can see past door and cave at start | 2019-05-15
| on restart, player should face right before entering scene again | ?
| Crystals do not shatter on mobile in crystal boss room after solving | ?
| Pause game on completion (timer keeps going, can move player) | ?
| can press pause at level complete screen (even paused screen) | 2019-11-11
| restart on boss fight is buggy | 2019-11-11
| Stalactite rubble doesn't disappear | 2019-11-11
| Player enters boss levels twice (plays entrance coroutine twice?) | 2019-11-11
| on death, all buttons are shown in the dropdown menu | 2019-11-16
| on restart, the player should reset properly (e.g. retry on death bugs out) | 2019-11-16
| hypersonic was not being accessed properly | 2019-11-16
| crystal boss - so many moth essence. clean this up. | 2019-11-16
| Loading screen - removed moth | 2019-11-16
| Reset fog | 2019-11-17
| Clear spider webs on reset | 2019-11-17
| Boss moths don't disappear on restart | 2019-11-17
| Check triggers are reset properly | 2019-11-17
| Stats screen to be implemented | 2019-11-23
| Stat tracking (distance, durations etc) to be implemented | 2019-11-24
| sometimes on boss levels, jump gets stuck | 2019-11-24
| couritine on boss level to shut doors and start boss - keeps running on restart | 2019-11-24
| Main Menu title screen: Clicking "options" after "play" is buggy (switch screens) | 2019-11-24
| boss levels need to disable fog | 2019-11-25
| clumsy doesn’t show up on startup in menu | 2019-11-25
| Check level stars show up - refresh after level complete? | 2019-11-26
| switching to level select from menu - clumsy needs to follow, camera shouldn't slide | 2019-11-26
| Level select scrolling to go back to start to hide the end of the content window | 2019-11-26